## log
4.09.2021
7:30 PM - 8:00 PM | Went Through & Understood API & JSON fields.
8:10 PM - 8:25 PM | Did some Whiteboarding of the UI.
8:30 PM - 10:00 PM | Project Init & created some rough barebone structure to go
9:00 PM - 9:30 PM | Completed Container & Search Component.
9:30 PM - 11: 00 PM | Faced CORS issue, Did some research, Created Proxy server in Node.js to Bypass it.
5.09.2021
11:35 - 12:30 PM | Worked on ProfilePage & Profile Component. Went Through Bootstrap.
6:00 PM - 8:00 PM | Worked On ProfilePic, Social Component.
10:00 PM - 11:30 PM | Worked on Card Designs & Other Components.
6.09.2021
9:00 - 10:30 | Created Theme for better styling, played with some colors. Did Some UI Changes.
11: 00 - 12:30 PM | Faced some issues in commit (ENOENT : File Not Found), did some research, then used rebasing to tackle them.
7.09.2021
10:30 - 11 : 20 | Created routes for Home, Profile, & Job Page.
11: 00 - 12:30 PM | Faced some issues in commit (ENOENT : File Not Found), did some research, then used rebasing to tackle them.
2:00 PM - 2: 30 PM | Updated Search component to use it in both Profile & Job Page.
2: 40 PM - 3 : 50 PM | Worked on Job Page. Created Job Item, Job Details, Job Expectations, Job Members Page.
4 : 10 PM - 4 : 30 | Included Final Skills & Experience Section & Dropped Older Placeholder (Profile 3rd Card).
5: 00 PM - 5 : 20 PM | Created Heroku Dyno for deployment & Deployed for Test run.